## Stream1
Stream | Domain | Milestone Name | Planned Start Date | Planned End Date | Actual Completion | % Completion | Task Status | Delay Flag | Delay Reason | Owner / SME | Last Updated
Stream 1 | Occupational Health & Welfare | Incident List Received | 2025-06-19 | 2025-06-29 | 2025-06-26 | 88 | On Track | No |  | Mehak Javed | 2025-07-16
Stream 1 | Occupational Health & Welfare | Data Validated | 2025-07-01 | 2025-07-11 | 2025-07-09 | 70 | At Risk | No |  | Zoya Malik | 2025-07-12
Stream 1 | Occupational Health & Welfare | Data Model Built | 2025-06-24 | 2025-07-08 | 2025-07-05 | 77 | At Risk | No |  | Faizan Ahmed | 2025-07-13
Stream 1 | Occupational Health & Welfare | Mock Dashboard Designed | 2025-06-28 | 2025-07-06 | 2025-07-08 | 86 | Delayed | Yes | Technical issue | Umar Sheikh | 2025-07-16
Stream 1 | Occupational Health & Welfare | Dashboard Approved | 2025-06-24 | 2025-06-30 | 2025-06-30 | 83 | On Track | No |  | Hira Qureshi | 2025-07-17
Stream 1 | Environment | Incident List Received | 2025-06-30 | 2025-07-13 | 2025-07-13 | 79 | At Risk | No |  | Sana Khan | 2025-07-13
Stream 1 | Environment | Data Validated | 2025-06-22 | 2025-07-06 | 2025-07-06 | 96 | On Track | No |  | Ali Raza | 2025-07-16
Stream 1 | Environment | Data Model Built | 2025-06-26 | 2025-07-01 | 2025-07-09 | 77 | Delayed | Yes | Technical issue | Bilal Saeed | 2025-07-13
Stream 1 | Environment | Mock Dashboard Designed | 2025-06-24 | 2025-07-05 | 2025-07-02 | 71 | At Risk | No |  | Ali Raza | 2025-07-15
Stream 1 | Environment | Dashboard Approved | 2025-06-21 | 2025-07-05 | 2025-07-04 | 90 | On Track | No |  | Sana Khan | 2025-07-13
Stream 1 | Social Risk | Incident List Received | 2025-06-17 | 2025-06-24 | 2025-07-02 | 94 | Delayed | Yes | Rework requested | Umar Sheikh | 2025-07-12
Stream 1 | Social Risk | Data Validated | 2025-06-27 | 2025-07-06 | 2025-07-06 | 77 | At Risk | No |  | Sana Khan | 2025-07-16
Stream 1 | Social Risk | Data Model Built | 2025-06-26 | 2025-07-07 | 2025-07-07 | 71 | At Risk | No |  | Sana Khan | 2025-07-15
Stream 1 | Social Risk | Mock Dashboard Designed | 2025-06-30 | 2025-07-13 | 2025-07-12 | 81 | On Track | No |  | Mehak Javed | 2025-07-13
Stream 1 | Social Risk | Dashboard Approved | 2025-07-02 | 2025-07-12 | 2025-07-10 | 93 | On Track | No |  | Mehak Javed | 2025-07-13
Stream 1 | High-Risk Transport | Incident List Received | 2025-07-01 | 2025-07-10 | 2025-07-10 | 72 | At Risk | No |  | Umar Sheikh | 2025-07-15
Stream 1 | High-Risk Transport | Data Validated | 2025-06-20 | 2025-06-29 | 2025-06-28 | 80 | On Track | No |  | Bilal Saeed | 2025-07-15
Stream 1 | High-Risk Transport | Data Model Built | 2025-06-23 | 2025-07-07 | 2025-07-08 | 76 | Delayed | Yes | Pending stakeholder review | Sana Khan | 2025-07-17
Stream 1 | High-Risk Transport | Mock Dashboard Designed | 2025-06-23 | 2025-06-28 | 2025-07-05 | 69 | Delayed | Yes | Awaiting SME feedback | Umar Sheikh | 2025-07-13
Stream 1 | High-Risk Transport | Dashboard Approved | 2025-06-23 | 2025-07-03 | 2025-06-30 | 96 | On Track | No |  | Bilal Saeed | 2025-07-16
Stream 1 | Business Continuity | Incident List Received | 2025-06-26 | 2025-07-01 | 2025-07-01 | 68 | At Risk | No |  | Ali Raza | 2025-07-13
Stream 1 | Business Continuity | Data Validated | 2025-06-23 | 2025-06-29 | 2025-07-01 | 78 | Delayed | Yes | Late data submission | Hira Qureshi | 2025-07-14
Stream 1 | Business Continuity | Data Model Built | 2025-06-26 | 2025-07-05 | 2025-07-02 | 100 | On Track | No |  | Hira Qureshi | 2025-07-15
Stream 1 | Business Continuity | Mock Dashboard Designed | 2025-06-24 | 2025-07-03 | 2025-07-06 | 60 | Delayed | Yes | Rework requested | Ali Raza | 2025-07-13
Stream 1 | Business Continuity | Dashboard Approved | 2025-06-18 | 2025-07-01 | 2025-06-28 | 67 | At Risk | No |  | Bilal Saeed | 2025-07-16
Stream 1 | Crisis Management & Emergency Response | Incident List Received | 2025-06-22 | 2025-07-03 | 2025-07-09 | 67 | Delayed | Yes | Pending stakeholder review | Umar Sheikh | 2025-07-12
Stream 1 | Crisis Management & Emergency Response | Data Validated | 2025-06-27 | 2025-07-06 | 2025-07-03 | 93 | On Track | No |  | Faizan Ahmed | 2025-07-13
Stream 1 | Crisis Management & Emergency Response | Data Model Built | 2025-06-29 | 2025-07-04 | 2025-07-10 | 77 | Delayed | Yes | Technical issue | Mehak Javed | 2025-07-12
Stream 1 | Crisis Management & Emergency Response | Mock Dashboard Designed | 2025-06-19 | 2025-07-04 | 2025-07-02 | 68 | At Risk | No |  | Umar Sheikh | 2025-07-13
Stream 1 | Crisis Management & Emergency Response | Dashboard Approved | 2025-06-25 | 2025-07-08 | 2025-07-06 | 88 | On Track | No |  | Zoya Malik | 2025-07-13
Stream 1 | Process Safety | Incident List Received | 2025-06-28 | 2025-07-07 | 2025-07-05 | 75 | At Risk | No |  | Zoya Malik | 2025-07-17
Stream 1 | Process Safety | Data Validated | 2025-07-02 | 2025-07-10 | 2025-07-10 | 90 | On Track | No |  | Zoya Malik | 2025-07-14
Stream 1 | Process Safety | Data Model Built | 2025-06-30 | 2025-07-07 | 2025-07-07 | 67 | At Risk | No |  | Mehak Javed | 2025-07-16
Stream 1 | Process Safety | Mock Dashboard Designed | 2025-06-27 | 2025-07-04 | 2025-07-09 | 95 | Delayed | Yes | Rework requested | Umar Sheikh | 2025-07-16
Stream 1 | Process Safety | Dashboard Approved | 2025-06-22 | 2025-07-04 | 2025-07-02 | 64 | At Risk | No |  | Umar Sheikh | 2025-07-13
Stream 1 | Contractor & Projects | Incident List Received | 2025-06-24 | 2025-06-29 | 2025-06-26 | 85 | On Track | No |  | Faizan Ahmed | 2025-07-12
Stream 1 | Contractor & Projects | Data Validated | 2025-07-01 | 2025-07-06 |  | 14 | At Risk | No |  | Bilal Saeed | 2025-07-14
Stream 1 | Contractor & Projects | Data Model Built | 2025-06-29 | 2025-07-14 | 2025-07-12 | 61 | At Risk | No |  | Ali Raza | 2025-07-12
Stream 1 | Contractor & Projects | Mock Dashboard Designed | 2025-06-29 | 2025-07-13 | 2025-07-22 | 86 | Delayed | Yes | Late data submission | Mehak Javed | 2025-07-17
Stream 1 | Contractor & Projects | Dashboard Approved | 2025-06-25 | 2025-07-09 | 2025-07-09 | 81 | On Track | No |  | Hira Qureshi | 2025-07-14
Stream 1 | Personal Safety & Human Performance | Incident List Received | 2025-06-23 | 2025-07-06 | 2025-07-03 | 70 | At Risk | No |  | Faizan Ahmed | 2025-07-15
Stream 1 | Personal Safety & Human Performance | Data Validated | 2025-06-27 | 2025-07-06 | 2025-07-05 | 94 | On Track | No |  | Bilal Saeed | 2025-07-14
Stream 1 | Personal Safety & Human Performance | Data Model Built | 2025-06-19 | 2025-06-28 | 2025-06-25 | 73 | At Risk | No |  | Hira Qureshi | 2025-07-15
Stream 1 | Personal Safety & Human Performance | Mock Dashboard Designed | 2025-06-19 | 2025-06-26 | 2025-06-25 | 77 | At Risk | No |  | Mehak Javed | 2025-07-12
Stream 1 | Personal Safety & Human Performance | Dashboard Approved | 2025-06-20 | 2025-06-29 | 2025-07-08 | 70 | Delayed | Yes | Pending stakeholder review | Bilal Saeed | 2025-07-14
Stream 1 | Performance & Planning | Incident List Received | 2025-06-20 | 2025-06-28 | 2025-06-28 | 97 | On Track | No |  | Bilal Saeed | 2025-07-16
Stream 1 | Performance & Planning | Data Validated | 2025-06-26 | 2025-07-02 | 2025-06-29 | 71 | At Risk | No |  | Mehak Javed | 2025-07-15
Stream 1 | Performance & Planning | Data Model Built | 2025-06-27 | 2025-07-10 | 2025-07-10 | 67 | At Risk | No |  | Sana Khan | 2025-07-15
Stream 1 | Performance & Planning | Mock Dashboard Designed | 2025-07-02 | 2025-07-10 | 2025-07-09 | 65 | At Risk | No |  | Zoya Malik | 2025-07-12
Stream 1 | Performance & Planning | Dashboard Approved | 2025-06-30 | 2025-07-11 | 2025-07-17 | 78 | Delayed | Yes | Resource unavailability | Umar Sheikh | 2025-07-15

## Overall
Stream | Domain | Milestone Name | Planned Start Date | Planned End Date | Actual Completion | % Completion | Task Status | Delay Flag | Delay Reason | Owner / SME | Last Updated
Stream 2 | Occupational Health & Welfare | Workshop Completed | 2025-06-29 | 2025-07-05 | 2025-07-15 | 60 | Delayed | Yes | Awaiting SME feedback | Bilal Saeed | 2025-07-12
Stream 2 | Occupational Health & Welfare | BRD Drafted | 2025-06-28 | 2025-07-07 | 2025-07-05 | 62 | At Risk | No |  | Zoya Malik | 2025-07-17
Stream 2 | Occupational Health & Welfare | BRD Reviewed | 2025-06-21 | 2025-06-28 | 2025-06-25 | 92 | On Track | No |  | Ali Raza | 2025-07-14
Stream 2 | Occupational Health & Welfare | BRD Approved | 2025-06-30 | 2025-07-14 | 2025-07-11 | 82 | On Track | No |  | Sana Khan | 2025-07-13
Stream 2 | Occupational Health & Welfare | Dashboard Designed | 2025-06-24 | 2025-07-07 | 2025-07-05 | 86 | On Track | No |  | Hira Qureshi | 2025-07-15
Stream 2 | Occupational Health & Welfare | Dashboard Built | 2025-06-20 | 2025-06-27 | 2025-07-03 | 90 | Delayed | Yes | Technical issue | Umar Sheikh | 2025-07-13
Stream 2 | Occupational Health & Welfare | Dashboard Released | 2025-06-21 | 2025-06-29 | 2025-06-28 | 82 | On Track | No |  | Bilal Saeed | 2025-07-12
Stream 2 | Environment | Workshop Completed | 2025-06-18 | 2025-06-27 | 2025-07-05 | 77 | Delayed | Yes | Pending stakeholder review | Mehak Javed | 2025-07-17
Stream 2 | Environment | BRD Drafted | 2025-06-23 | 2025-07-01 | 2025-07-06 | 83 | Delayed | Yes | Technical issue | Hira Qureshi | 2025-07-16
Stream 2 | Environment | BRD Reviewed | 2025-07-01 | 2025-07-11 | 2025-07-10 | 91 | On Track | No |  | Sana Khan | 2025-07-16
Stream 2 | Environment | BRD Approved | 2025-06-22 | 2025-07-04 | 2025-07-01 | 71 | At Risk | No |  | Hira Qureshi | 2025-07-15
Stream 2 | Environment | Dashboard Designed | 2025-06-18 | 2025-06-29 | 2025-06-28 | 77 | At Risk | No |  | Zoya Malik | 2025-07-12
Stream 2 | Environment | Dashboard Built | 2025-06-22 | 2025-06-30 | 2025-06-27 | 81 | On Track | No |  | Ali Raza | 2025-07-15
Stream 2 | Environment | Dashboard Released | 2025-06-21 | 2025-06-28 | 2025-06-30 | 70 | Delayed | Yes | Late data submission | Bilal Saeed | 2025-07-13
Stream 2 | Social Risk | Workshop Completed | 2025-06-20 | 2025-07-04 | 2025-07-09 | 92 | Delayed | Yes | Pending stakeholder review | Sana Khan | 2025-07-16
Stream 2 | Social Risk | BRD Drafted | 2025-06-26 | 2025-07-05 | 2025-07-09 | 69 | Delayed | Yes | Rework requested | Sana Khan | 2025-07-17
Stream 2 | Social Risk | BRD Reviewed | 2025-06-26 | 2025-07-03 | 2025-06-30 | 67 | At Risk | No |  | Zoya Malik | 2025-07-14
Stream 2 | Social Risk | BRD Approved | 2025-07-02 | 2025-07-07 | 2025-07-05 | 63 | At Risk | No |  | Mehak Javed | 2025-07-14
Stream 2 | Social Risk | Dashboard Designed | 2025-06-24 | 2025-07-07 |  | 70 | Delayed | Yes | Pending stakeholder review | Ali Raza | 2025-07-16
Stream 2 | Social Risk | Dashboard Built | 2025-06-17 | 2025-06-26 |  | 29 | Delayed | Yes | Late data submission | Bilal Saeed | 2025-07-16
Stream 2 | Social Risk | Dashboard Released | 2025-06-18 | 2025-06-24 | 2025-06-23 | 79 | At Risk | No |  | Faizan Ahmed | 2025-07-17
Stream 2 | High-Risk Transport | Workshop Completed | 2025-06-28 | 2025-07-11 | 2025-07-10 | 86 | On Track | No |  | Ali Raza | 2025-07-13
Stream 2 | High-Risk Transport | BRD Drafted | 2025-07-01 | 2025-07-13 |  | 61 | Delayed | Yes | Late data submission | Faizan Ahmed | 2025-07-16
Stream 2 | High-Risk Transport | BRD Reviewed | 2025-06-29 | 2025-07-11 | 2025-07-11 | 67 | At Risk | No |  | Hira Qureshi | 2025-07-13
Stream 2 | High-Risk Transport | BRD Approved | 2025-07-02 | 2025-07-11 | 2025-07-19 | 79 | Delayed | Yes | Resource unavailability | Hira Qureshi | 2025-07-13
Stream 2 | High-Risk Transport | Dashboard Designed | 2025-06-19 | 2025-07-02 | 2025-07-06 | 77 | Delayed | Yes | Late data submission | Hira Qureshi | 2025-07-16
Stream 2 | High-Risk Transport | Dashboard Built | 2025-06-26 | 2025-07-04 | 2025-07-12 | 77 | Delayed | Yes | Resource unavailability | Hira Qureshi | 2025-07-17
Stream 2 | High-Risk Transport | Dashboard Released | 2025-06-19 | 2025-06-26 | 2025-06-23 | 86 | On Track | No |  | Bilal Saeed | 2025-07-15
Stream 2 | Business Continuity | Workshop Completed | 2025-06-26 | 2025-07-07 | 2025-07-04 | 88 | On Track | No |  | Sana Khan | 2025-07-17
Stream 2 | Business Continuity | BRD Drafted | 2025-06-18 | 2025-07-03 | 2025-06-30 | 94 | On Track | No |  | Faizan Ahmed | 2025-07-14
Stream 2 | Business Continuity | BRD Reviewed | 2025-06-26 | 2025-07-06 | 2025-07-03 | 92 | On Track | No |  | Sana Khan | 2025-07-13
Stream 2 | Business Continuity | BRD Approved | 2025-06-25 | 2025-06-30 | 2025-07-04 | 86 | Delayed | Yes | Resource unavailability | Umar Sheikh | 2025-07-17
Stream 2 | Business Continuity | Dashboard Designed | 2025-06-23 | 2025-07-05 | 2025-07-03 | 99 | On Track | No |  | Ali Raza | 2025-07-15
Stream 2 | Business Continuity | Dashboard Built | 2025-06-23 | 2025-06-29 | 2025-06-28 | 60 | At Risk | No |  | Ali Raza | 2025-07-13
Stream 2 | Business Continuity | Dashboard Released | 2025-06-26 | 2025-07-04 | 2025-07-03 | 64 | At Risk | No |  | Faizan Ahmed | 2025-07-14
Stream 2 | Crisis Management & Emergency Response | Workshop Completed | 2025-06-26 | 2025-07-02 | 2025-07-12 | 100 | Delayed | Yes | Technical issue | Mehak Javed | 2025-07-17
Stream 2 | Crisis Management & Emergency Response | BRD Drafted | 2025-06-19 | 2025-07-02 | 2025-06-30 | 74 | At Risk | No |  | Mehak Javed | 2025-07-12
Stream 2 | Crisis Management & Emergency Response | BRD Reviewed | 2025-07-01 | 2025-07-08 | 2025-07-06 | 91 | On Track | No |  | Sana Khan | 2025-07-17
Stream 2 | Crisis Management & Emergency Response | BRD Approved | 2025-06-30 | 2025-07-12 | 2025-07-16 | 97 | Delayed | Yes | Late data submission | Mehak Javed | 2025-07-15
Stream 2 | Crisis Management & Emergency Response | Dashboard Designed | 2025-06-21 | 2025-07-02 | 2025-06-29 | 82 | On Track | No |  | Faizan Ahmed | 2025-07-17
Stream 2 | Crisis Management & Emergency Response | Dashboard Built | 2025-06-20 | 2025-07-03 |  | 61 | Delayed | Yes | Resource unavailability | Umar Sheikh | 2025-07-17
Stream 2 | Crisis Management & Emergency Response | Dashboard Released | 2025-06-21 | 2025-07-01 | 2025-07-03 | 80 | Delayed | Yes | Awaiting SME feedback | Bilal Saeed | 2025-07-12
Stream 2 | Process Safety | Workshop Completed | 2025-06-17 | 2025-06-25 | 2025-06-30 | 82 | Delayed | Yes | Resource unavailability | Sana Khan | 2025-07-17
Stream 2 | Process Safety | BRD Drafted | 2025-06-29 | 2025-07-14 | 2025-07-21 | 74 | Delayed | Yes | Technical issue | Ali Raza | 2025-07-15
Stream 2 | Process Safety | BRD Reviewed | 2025-06-25 | 2025-07-05 | 2025-07-03 | 91 | On Track | No |  | Faizan Ahmed | 2025-07-12
Stream 2 | Process Safety | BRD Approved | 2025-06-28 | 2025-07-13 | 2025-07-15 | 92 | Delayed | Yes | Awaiting SME feedback | Ali Raza | 2025-07-13
Stream 2 | Process Safety | Dashboard Designed | 2025-06-30 | 2025-07-08 | 2025-07-08 | 79 | At Risk | No |  | Sana Khan | 2025-07-15
Stream 2 | Process Safety | Dashboard Built | 2025-06-18 | 2025-07-02 | 2025-06-30 | 91 | On Track | No |  | Sana Khan | 2025-07-15
Stream 2 | Process Safety | Dashboard Released | 2025-06-24 | 2025-07-05 | 2025-07-03 | 77 | At Risk | No |  | Bilal Saeed | 2025-07-16
Stream 2 | Contractor & Projects | Workshop Completed | 2025-06-30 | 2025-07-09 | 2025-07-08 | 93 | On Track | No |  | Sana Khan | 2025-07-16
Stream 2 | Contractor & Projects | BRD Drafted | 2025-06-21 | 2025-07-02 | 2025-07-02 | 99 | On Track | No |  | Zoya Malik | 2025-07-16
Stream 2 | Contractor & Projects | BRD Reviewed | 2025-07-02 | 2025-07-12 | 2025-07-19 | 66 | Delayed | Yes | Rework requested | Zoya Malik | 2025-07-12
Stream 2 | Contractor & Projects | BRD Approved | 2025-06-29 | 2025-07-05 | 2025-07-05 | 92 | On Track | No |  | Bilal Saeed | 2025-07-16
Stream 2 | Contractor & Projects | Dashboard Designed | 2025-06-28 | 2025-07-05 | 2025-07-15 | 93 | Delayed | Yes | Resource unavailability | Hira Qureshi | 2025-07-13
Stream 2 | Contractor & Projects | Dashboard Built | 2025-06-30 | 2025-07-13 | 2025-07-10 | 84 | On Track | No |  | Sana Khan | 2025-07-17
Stream 2 | Contractor & Projects | Dashboard Released | 2025-06-23 | 2025-06-29 | 2025-06-29 | 93 | On Track | No |  | Ali Raza | 2025-07-17
Stream 2 | Personal Safety & Human Performance | Workshop Completed | 2025-06-29 | 2025-07-04 | 2025-07-04 | 93 | On Track | No |  | Umar Sheikh | 2025-07-16
Stream 2 | Personal Safety & Human Performance | BRD Drafted | 2025-06-30 | 2025-07-12 | 2025-07-10 | 86 | On Track | No |  | Bilal Saeed | 2025-07-15
Stream 2 | Personal Safety & Human Performance | BRD Reviewed | 2025-06-23 | 2025-07-04 | 2025-07-01 | 84 | On Track | No |  | Hira Qureshi | 2025-07-13
Stream 2 | Personal Safety & Human Performance | BRD Approved | 2025-06-22 | 2025-07-05 | 2025-07-04 | 76 | At Risk | No |  | Umar Sheikh | 2025-07-13
Stream 2 | Personal Safety & Human Performance | Dashboard Designed | 2025-06-30 | 2025-07-09 | 2025-07-06 | 91 | On Track | No |  | Faizan Ahmed | 2025-07-14
Stream 2 | Personal Safety & Human Performance | Dashboard Built | 2025-07-01 | 2025-07-07 | 2025-07-07 | 65 | At Risk | No |  | Umar Sheikh | 2025-07-17
Stream 2 | Personal Safety & Human Performance | Dashboard Released | 2025-06-18 | 2025-06-29 | 2025-06-27 | 60 | At Risk | No |  | Zoya Malik | 2025-07-14
Stream 2 | Performance & Planning | Workshop Completed | 2025-06-19 | 2025-07-04 | 2025-07-07 | 68 | Delayed | Yes | Awaiting SME feedback | Sana Khan | 2025-07-16
Stream 2 | Performance & Planning | BRD Drafted | 2025-06-20 | 2025-06-28 | 2025-07-05 | 91 | Delayed | Yes | Pending stakeholder review | Hira Qureshi | 2025-07-12
Stream 2 | Performance & Planning | BRD Reviewed | 2025-06-29 | 2025-07-11 | 2025-07-10 | 99 | On Track | No |  | Hira Qureshi | 2025-07-16
Stream 2 | Performance & Planning | BRD Approved | 2025-06-27 | 2025-07-09 | 2025-07-06 | 93 | On Track | No |  | Hira Qureshi | 2025-07-12
Stream 2 | Performance & Planning | Dashboard Designed | 2025-06-21 | 2025-06-27 | 2025-06-27 | 86 | On Track | No |  | Faizan Ahmed | 2025-07-15
Stream 2 | Performance & Planning | Dashboard Built | 2025-06-24 | 2025-07-05 | 2025-07-04 | 72 | At Risk | No |  | Mehak Javed | 2025-07-12
Stream 2 | Performance & Planning | Dashboard Released | 2025-06-18 | 2025-06-30 |  | 69 | Delayed | Yes | Pending stakeholder review | Mehak Javed | 2025-07-16
Stream 1 | Occupational Health & Welfare | Incident List Received | 2025-06-19 | 2025-06-29 | 2025-06-26 | 88 | On Track | No |  | Mehak Javed | 2025-07-16
Stream 1 | Occupational Health & Welfare | Data Validated | 2025-07-01 | 2025-07-11 | 2025-07-09 | 70 | At Risk | No |  | Zoya Malik | 2025-07-12
Stream 1 | Occupational Health & Welfare | Data Model Built | 2025-06-24 | 2025-07-08 | 2025-07-05 | 77 | At Risk | No |  | Faizan Ahmed | 2025-07-13
Stream 1 | Occupational Health & Welfare | Mock Dashboard Designed | 2025-06-28 | 2025-07-06 | 2025-07-08 | 86 | Delayed | Yes | Technical issue | Umar Sheikh | 2025-07-16
Stream 1 | Occupational Health & Welfare | Dashboard Approved | 2025-06-24 | 2025-06-30 | 2025-06-30 | 83 | On Track | No |  | Hira Qureshi | 2025-07-17
Stream 1 | Environment | Incident List Received | 2025-06-30 | 2025-07-13 | 2025-07-13 | 79 | At Risk | No |  | Sana Khan | 2025-07-13
Stream 1 | Environment | Data Validated | 2025-06-22 | 2025-07-06 | 2025-07-06 | 96 | On Track | No |  | Ali Raza | 2025-07-16
Stream 1 | Environment | Data Model Built | 2025-06-26 | 2025-07-01 | 2025-07-09 | 77 | Delayed | Yes | Technical issue | Bilal Saeed | 2025-07-13
Stream 1 | Environment | Mock Dashboard Designed | 2025-06-24 | 2025-07-05 | 2025-07-02 | 71 | At Risk | No |  | Ali Raza | 2025-07-15
Stream 1 | Environment | Dashboard Approved | 2025-06-21 | 2025-07-05 | 2025-07-04 | 90 | On Track | No |  | Sana Khan | 2025-07-13
Stream 1 | Social Risk | Incident List Received | 2025-06-17 | 2025-06-24 | 2025-07-02 | 94 | Delayed | Yes | Rework requested | Umar Sheikh | 2025-07-12
Stream 1 | Social Risk | Data Validated | 2025-06-27 | 2025-07-06 | 2025-07-06 | 77 | At Risk | No |  | Sana Khan | 2025-07-16
Stream 1 | Social Risk | Data Model Built | 2025-06-26 | 2025-07-07 | 2025-07-07 | 71 | At Risk | No |  | Sana Khan | 2025-07-15
Stream 1 | Social Risk | Mock Dashboard Designed | 2025-06-30 | 2025-07-13 | 2025-07-12 | 81 | On Track | No |  | Mehak Javed | 2025-07-13
Stream 1 | Social Risk | Dashboard Approved | 2025-07-02 | 2025-07-12 | 2025-07-10 | 93 | On Track | No |  | Mehak Javed | 2025-07-13
Stream 1 | High-Risk Transport | Incident List Received | 2025-07-01 | 2025-07-10 | 2025-07-10 | 72 | At Risk | No |  | Umar Sheikh | 2025-07-15
Stream 1 | High-Risk Transport | Data Validated | 2025-06-20 | 2025-06-29 | 2025-06-28 | 80 | On Track | No |  | Bilal Saeed | 2025-07-15
Stream 1 | High-Risk Transport | Data Model Built | 2025-06-23 | 2025-07-07 | 2025-07-08 | 76 | Delayed | Yes | Pending stakeholder review | Sana Khan | 2025-07-17
Stream 1 | High-Risk Transport | Mock Dashboard Designed | 2025-06-23 | 2025-06-28 | 2025-07-05 | 69 | Delayed | Yes | Awaiting SME feedback | Umar Sheikh | 2025-07-13
Stream 1 | High-Risk Transport | Dashboard Approved | 2025-06-23 | 2025-07-03 | 2025-06-30 | 96 | On Track | No |  | Bilal Saeed | 2025-07-16
Stream 1 | Business Continuity | Incident List Received | 2025-06-26 | 2025-07-01 | 2025-07-01 | 68 | At Risk | No |  | Ali Raza | 2025-07-13
Stream 1 | Business Continuity | Data Validated | 2025-06-23 | 2025-06-29 | 2025-07-01 | 78 | Delayed | Yes | Late data submission | Hira Qureshi | 2025-07-14
Stream 1 | Business Continuity | Data Model Built | 2025-06-26 | 2025-07-05 | 2025-07-02 | 100 | On Track | No |  | Hira Qureshi | 2025-07-15
Stream 1 | Business Continuity | Mock Dashboard Designed | 2025-06-24 | 2025-07-03 | 2025-07-06 | 60 | Delayed | Yes | Rework requested | Ali Raza | 2025-07-13
Stream 1 | Business Continuity | Dashboard Approved | 2025-06-18 | 2025-07-01 | 2025-06-28 | 67 | At Risk | No |  | Bilal Saeed | 2025-07-16
Stream 1 | Crisis Management & Emergency Response | Incident List Received | 2025-06-22 | 2025-07-03 | 2025-07-09 | 67 | Delayed | Yes | Pending stakeholder review | Umar Sheikh | 2025-07-12
Stream 1 | Crisis Management & Emergency Response | Data Validated | 2025-06-27 | 2025-07-06 | 2025-07-03 | 93 | On Track | No |  | Faizan Ahmed | 2025-07-13
Stream 1 | Crisis Management & Emergency Response | Data Model Built | 2025-06-29 | 2025-07-04 | 2025-07-10 | 77 | Delayed | Yes | Technical issue | Mehak Javed | 2025-07-12
Stream 1 | Crisis Management & Emergency Response | Mock Dashboard Designed | 2025-06-19 | 2025-07-04 | 2025-07-02 | 68 | At Risk | No |  | Umar Sheikh | 2025-07-13
Stream 1 | Crisis Management & Emergency Response | Dashboard Approved | 2025-06-25 | 2025-07-08 | 2025-07-06 | 88 | On Track | No |  | Zoya Malik | 2025-07-13
Stream 1 | Process Safety | Incident List Received | 2025-06-28 | 2025-07-07 | 2025-07-05 | 75 | At Risk | No |  | Zoya Malik | 2025-07-17
Stream 1 | Process Safety | Data Validated | 2025-07-02 | 2025-07-10 | 2025-07-10 | 90 | On Track | No |  | Zoya Malik | 2025-07-14
Stream 1 | Process Safety | Data Model Built | 2025-06-30 | 2025-07-07 | 2025-07-07 | 67 | At Risk | No |  | Mehak Javed | 2025-07-16
Stream 1 | Process Safety | Mock Dashboard Designed | 2025-06-27 | 2025-07-04 | 2025-07-09 | 95 | Delayed | Yes | Rework requested | Umar Sheikh | 2025-07-16
Stream 1 | Process Safety | Dashboard Approved | 2025-06-22 | 2025-07-04 | 2025-07-02 | 64 | At Risk | No |  | Umar Sheikh | 2025-07-13
Stream 1 | Contractor & Projects | Incident List Received | 2025-06-24 | 2025-06-29 | 2025-06-26 | 85 | On Track | No |  | Faizan Ahmed | 2025-07-12
Stream 1 | Contractor & Projects | Data Validated | 2025-07-01 | 2025-07-06 |  | 14 | At Risk | No |  | Bilal Saeed | 2025-07-14
Stream 1 | Contractor & Projects | Data Model Built | 2025-06-29 | 2025-07-14 | 2025-07-12 | 61 | At Risk | No |  | Ali Raza | 2025-07-12
Stream 1 | Contractor & Projects | Mock Dashboard Designed | 2025-06-29 | 2025-07-13 | 2025-07-22 | 86 | Delayed | Yes | Late data submission | Mehak Javed | 2025-07-17
Stream 1 | Contractor & Projects | Dashboard Approved | 2025-06-25 | 2025-07-09 | 2025-07-09 | 81 | On Track | No |  | Hira Qureshi | 2025-07-14
Stream 1 | Personal Safety & Human Performance | Incident List Received | 2025-06-23 | 2025-07-06 | 2025-07-03 | 70 | At Risk | No |  | Faizan Ahmed | 2025-07-15
Stream 1 | Personal Safety & Human Performance | Data Validated | 2025-06-27 | 2025-07-06 | 2025-07-05 | 94 | On Track | No |  | Bilal Saeed | 2025-07-14
Stream 1 | Personal Safety & Human Performance | Data Model Built | 2025-06-19 | 2025-06-28 | 2025-06-25 | 73 | At Risk | No |  | Hira Qureshi | 2025-07-15
Stream 1 | Personal Safety & Human Performance | Mock Dashboard Designed | 2025-06-19 | 2025-06-26 | 2025-06-25 | 77 | At Risk | No |  | Mehak Javed | 2025-07-12
Stream 1 | Personal Safety & Human Performance | Dashboard Approved | 2025-06-20 | 2025-06-29 | 2025-07-08 | 70 | Delayed | Yes | Pending stakeholder review | Bilal Saeed | 2025-07-14
Stream 1 | Performance & Planning | Incident List Received | 2025-06-20 | 2025-06-28 | 2025-06-28 | 97 | On Track | No |  | Bilal Saeed | 2025-07-16
Stream 1 | Performance & Planning | Data Validated | 2025-06-26 | 2025-07-02 | 2025-06-29 | 71 | At Risk | No |  | Mehak Javed | 2025-07-15
Stream 1 | Performance & Planning | Data Model Built | 2025-06-27 | 2025-07-10 | 2025-07-10 | 67 | At Risk | No |  | Sana Khan | 2025-07-15
Stream 1 | Performance & Planning | Mock Dashboard Designed | 2025-07-02 | 2025-07-10 | 2025-07-09 | 65 | At Risk | No |  | Zoya Malik | 2025-07-12
Stream 1 | Performance & Planning | Dashboard Approved | 2025-06-30 | 2025-07-11 | 2025-07-17 | 78 | Delayed | Yes | Resource unavailability | Umar Sheikh | 2025-07-15